## Slide 1: Moving Forward With FIDIC Suite of Contracts
1999 REVISION AND ONWARDS
BİLGE
MÜFTÜOĞLU

## Slide 2
Taking Over of Parts of the Works
Silver Book 1999 Revision Sub-Clause 10.2 [Taking Over of Parts the Works]
«Parts of the Works (other than Sections) shall not be taken over or used by the Employer, except as may be stated in the Employer’s Requirements or as may be agreed by both Parties»
BUT WHAT IF THEY DID?

## Slide 3
Silver Book 1999 Revision
Sub-Clause 17.2 [Contractors Care of the Works]
      1st paragraph:
      «The Contractor shall take full responsibility for the care of the Works and Goods from the Commencement Date until the Taking Over Certificate is issued (or is deemed to be issued under Sub-Clause 10.1 [Taking Over of the Works and Sections]) for the Works, when responsibility for the care of the Works shall pass to the Employer […]»
      3rd paragraph:
      «If any loss or damage happens to the Works, Goods or Contractor’s Documents during the period when the Contractor is responsible for their care, from any cause not listed in Sub-Clause 17.3 [Employer’s Risks], the Contractor shall rectify the loss or damage caused at the Contractor’s risk and cost.»

## Slide 4
Literal interpretation
Wording of Sub-Clause 10.2 [Taking Over of Parts of the Works]
  1999 Revision: possible different interpretations under different legal systems
  2017 Revision: clarification via incorporation of “use or occupation by the Employer of any part of the Permanent Works, except as may be specified in the Contract” into Sub-Clause 17.2 [Liability for Care of the Works] among the exceptions to the Contractor’s liability for care of the Works.
would not lead to a fair or even legally possible outcome.

## Slide 5
Design by Employer
Yellow Book 1999 Revision: “design of any part of the Works by the Employer's Personnel or by others for whom the Employer is responsible, if any” is deemed a risk item pursuant to Sub-Clause 17.3 (g) [Employer’s Risks].
Silver Book 1999 Revision: No mention of such incident as a risk item under the Employer’s liability area.
  Turnkey contract logic
  Sub-Clause 17.2 [Contractor’s Care of Works] & Sub-Clause 17.3 [Employer’s Risks]

## Slide 6
Would the Contractor be liable for the design prepared by the Employer?
2017 Revision included the “fault, error, defect or omission in any element of design of the Works by the Employer, other than design carried out by the Contractor in accordance with the Contractors’ obligations under the Contract” in the exceptions listed under Sub-Clause 17.2 [Liability for Care of the Works].

## Slide 7
Currently
Sub-Clauses 10.2 [Taking Over of Parts of the Works] & 17.2 [Liability for Care of the Works], as amended with 2017 Revision:
  well balanced and adequate, concludes on liability fairly
  in line with Golden Principle 3
  comply with common principle of law: “no one can benefit from its own default”
  worth to be reflected into contracts subject to Silver Book 1999 Revision
  serves as an interpretative guide to adjudicators and arbitrators in resolution of disputes arising out of 1999 Revision bearing the original wording.

## Slide 8
Sub-Clause 13.2 [Value Engineering]: The Contractor may, at any time, submit a written proposal to the Engineer for the benefit of the project and the Employer.
  the Engineer shall respond «as soon as practicable»
  the Contractor shall not delay Works while waiting a response
  no reference to «Review Period»
Proposals for Value Engineering

## Slide 9
Deeming Provisions:
  introduced with 2017 Revision
  solution to the Engineer’s silence to protect the Contractor from waiting for an indefinite period of time
  “Review Period” & “No-objection”

## Slide 10
Sub-Clause 5.2.3 (c) (YB-SB) & Sub-Clause 4.1 (d) (RB) under 2017 Revision:
  [Construction]:
  “the Contractor may modify any design or Contractor’s Documents which have previously been submitted for Review, by giving a Notice to the Engineer with reasons”
Problem
Contractor’s risk of facing delay when submitting a proposal under Sub-Clause 13.2 [Value Engineering]

## Slide 11
Sub-Clause 5.2 (YB-SB) & Sub-Clause 4.4 (RB) [Contractor’s Documents]:
  As Built Records and Operation and Maintenance Manuals,
  The documents specified in the ERQ or in the Specification,
  The documents required to satisfy permits, licenses and other regulatory approvals under the Contractor’s liability.
No reference to Sub-Clause 13.2 [Value Engineering]

## Slide 12
Ideas for Solution
Deemed Approval
  mentioning the proposals under Sub-Clause 13.2 [Value Engineering] among Contractor’s Documents, to provide a link to deemed approval
  if such link is already existent, a clarification via a reference to Sub-Clause 13.2 [Value Engineering] explicitly stating that the Engineer shall respond within the Review Period
OR
Deemed Rejection
  allowing the Contractor to deem its proposal rejected in the absence of a response from the Engineer within the Review Period

## Slide 13
Expelling Contractor from Site
Consequences of termination by Employer
1999 Revision Sub-Clause 15.2 [Termination by Employer] : “[…] the Employer may, upon giving 14 days’ notice to the Contractor, terminate the Contract and expel the Contractor from the Site”
2017 Revision Sub-Clause 15.2.3 (c) [After termination]: “the Contractor shall leave the Site and, if the Contractor does not do so, the Employer shall have the right to expel the Contractor from the Site”

## Slide 14
What to do, if the Contractor refrains from leaving?
Turkish law perspective
Law on Prevention of Violation of Immovable Property Possession nr 3091:
  the legal possessor of a land
  prevention of trespass via a decision from the governorate and with the executive force of enforcement officers
  without losing severe time

## Slide 15
IN CASE OF A CONTRACTUAL RELATIONSHIP, ONLY JUDICIAL BODIES ARE COMPETENT!
Although unusual, based on an experience
Adverse effects may even extend to any settlement negotiations

## Slide 16
Problem
Employer’s risk of facing delay and damages in case the Contractor rejects to vacate the Site upon termination, since the Contractor cannot be physically forced to leave the Site
Ideas for Solution
Imposition of liquidated damages for each day that the Contractor refrains from leaving the Site
Penalty provisions, if permitted by the governing law, through Particular Conditions

## Slide 17
Thank you