## Slide 1: Dispute Avoidance on Live Construction Projects

## Slide 2
Ambiguity
Disagreement
Dispute

## Slide 3
Clarity
Agreement
No Dispute

## Slide 4
Site
Action
(easy)
Action:
Mediation
Arbitration
Litigation
Action:
Settlement
Negotiations
Ambiguity
Disagreement
Dispute
Clarity
Agreement
No Dispute

## Slide 5
What was planned?
What actually happened?
Documentation and Processes

## Slide 6
What was planned?

## Slide 7
“Everything should be made as simple as possible, but not simpler.” Albert Einstein

## Slide 8: Baseline Programme – Programming Perspective
Submit/approve as early as possible
The Data Date should be the project commencement date (i.e., no activity with actual progress)
A software with critical path calculation capability
100% of the scope of works including design, authority approvals, temporary works, mock-ups, procurement, manufacturing, installation, construction and commissioning
Easy to understand and monitor (i.e., single-trade activities reasonably broken down into areas)
Realistic project calendar (i.e., weekends, holidays, low productivity periods such as Ramadan, CNY)
Limited activity durations based on reliable productivity assumptions (e.g., max. 30 days)
No activity labelled as “TBC”, “TBD”, “Tentative” etc.
Appropriate use of logic links (i.e., resource constraints and physical constraints only, no discretionary links and/or open ended activities)
A clear, continuous and dynamic critical path (e.g., no unnecessary interim activity constraints)
Resource assignments (i.e., manhours) cross-checked with historical data on a holistic basis
No contingency activity (i.e., contingency durations should be incorporated into the productivity assumptions)
Effective communication and collaboration with all internal and external stakeholders

## Slide 9: Baseline Programme – Project Management Perspective
Sufficient time for the activities carried out by Others
  Provision of site access
  Statutory approvals from authorities
  Design/`material approvals
  Works carried out by other contractors
Clear definitions for the interim project milestones and the final completion date (e.g., operation start, category A/B/C punch list items, temporary occupation permit, certificate of statutory completion)
Project management tools with reference to the programme (e.g., S-curves, manpower/equipment charts)
A programme narrative (e.g., key assumptions and interfaces, drawings, method statements, flowline diagrams, programme risks)
Revised programme(s) to consider:
  Changes to the scope of works (e.g., variation order)
  Changes to the planned sequence of the works (e.g., partially affecting design issues)
  Changes to the planned rate of progress (e.g., Covid-19)
  Mitigation of delays (e.g., acceleration programme, recovery programme)
  Incorporation of the actual delays which cannot be mitigated (i.e., extended project duration but not necessarily an “Extension of Time”)
  Agreement by parties in relation to deviations from the original baseline programme
  Upon agreement by parties, incorporation of the revised programme(s) for monitoring

## Slide 10
What actually happened?

## Slide 11
“Defer no time, delays have dangerous ends.”
William Shakespeare

## Slide 12: Progress Records
Parties’ agreement in relation to:
  Type
  Frequency
  Content
  Format
  Approval process
Progress of all the off-site and on-site works (i.e., including design and procurement)
Compatible work breakdown structure to the programme
Review of inconsistencies and discrepancies between different records on a regular basis

## Slide 13: Programming Updates
Parties’ agreement on the actual progress, or documentation of reasons for differences
Regular intervals based on progress report cut-off dates
No overriding of electronic copies
No discretionary modifications to the logic links and/or remaining activity durations
Issuance of a revised programme, if there are major deviations to the planned progress
Monitoring system for resource utilization
Effective communication and collaboration with all internal and external stakeholders

## Slide 14: Daily Site Reports (Raw data)
Weather
Manpower and major equipment list
Site access / handover information
Construction works in progress (i.e., trade and area)
Work stoppages and reasons (i.e., trade and area)
Key material deliveries
Key design issuances
Start / finish of the key activities on site (e.g., testing and commissioning)
Progress photos of key activities on site (e.g., completion of tower crane installation)
Discovery of delay events (e.g., water leakage affecting foundation works)
Resolution of delay events (e.g., completion of water leakage repair works)

## Slide 15: Weekly/Monthly Progress Reports (Compiled data)
1-page dashboard containing overall status of the works
Easy to read and understand (i.e., no unnecessary details and/or long narratives)
Key design submission / approval dates with reference to the programme
Key procurement dates with reference to the programme
Progress percentages of ongoing construction works with reference to the programme
Contemporaneous view on the critical path and the critical works that are being prioritized
Updated S-Curves and manpower/equipment charts with reference to the programme
Color coded progress drawings
Status of major project milestones, partial taking over certificates
Risk register (i.e., likelihood of risks, likely time/cost impact and preventative actions to be taken)
Issue log (i.e., status of issues, time/cost impact and mitigation actions to be taken)
Claims Log (i.e., delay notices and responses, status of claim submissions)

## Slide 16
Thank you